## Sheet1
Task | Task description
Business Case | To develop the business case document, justifying why we are undertaking this project.
Requirements gathering | To undertake a variety of requirements gathering techniques and activities and recording the raw results, for the purpose of developing project documentation.
Requirements Analysis | To analyse and conclude results from the requirements gathering phse, which will describe what requirements and objectives this project and its end user needs.
Create Requirements Document | To produce a document containing the results and conclusions from the requirements analysis.
Define key stakeholders | To produce documents defining and categorising our stakeholders of the project; e.g. end users, investors, persons involved, etc…
Project Charter | To develop the project charter document.
Resource allocations | To develop the guiding document for allocating resources, both financial and personnel.
Project Scope Statement | Develop the document detailing the boundaries and limits of the project's development and scope.
Develop WBS | Create a series of documents which highlight all tasks and activities involved in the project development life cycle
Create Sitemap | To develop documents containing information about the pages and resources to be used on the website project, and the relationships between them.
Create Wireframes/Mock-up | To develop a variety of models, both wireframes and mock-ups, to prototype the structure and relationships between components of the website project.
Interview & Obtain Stakeholder Approval | To interview all relevant stakeholders to obtain their opinion, perspective and ultimately their approval of our current understanding of the project requirements and needs and our plans for the project's development.
Choose tools/tech | To consult our team and make a selection of the most appropriate tools and software which we will use to develop our project in each of its phases.
UX Design Documentation | Develop a document which details UI design, user flows for users and functionality for our development team.
Select Content | To select all the possible content that will be used in the website, e.g. images, text, graphics, videos, etc…
Create page layout | Models and documents detailing the placement and arrangement of website content e.g. text, images, videos, graphics, etc…
Stakeholder Meeting | To hold a meeting with our contracted company and their appropriate stakeholders (e.g. administrators) in order to verify our current progress and plans for the project product. Their opinions and requests will be recorded and evaluated later.
Implement changes | To review and implement the appropriate record stakeholder requests, given that they heed to our project scope.
Develop models | Some more models detailing the UX, website structures and prototypes may be required for our project teams for effective project development.
Select Visual themes & Color palete | Visual themes of the website should decided in accordance with the contracted company image and the needs of the UX.
Content Management | Organise, optimise and format the content involved the project for our contractors benefit and their customers.
Coding | All coding activities that involved in the process of building the website and its server e.g. html, css, react, etc…
Debugging | All activities involved in debugging the written code so that the website is errorless and stable against exploits.
Browser Compatability Fixes | Implement changes and bug fixes involved in making the website more available on different browsers, such as chrome, firefox, smartphone browsers, etc...
Deploy website | Going through the series of activities involved in launching the website for public use.
Observe/record Major issues | To observer and record all issues reported on the devloper's and end-user's side of the website.
Test & upload website to server | To go through the series of activities involved in uploading the website to a server and testing it's stability.
Maintenance & updates | To actively monitor the website logs and implement fixes and changes over a long, as of yet undefined, period of time
Add user report system | To develop and implement a simple system that is apart of the website which allows the end-users (e.g. customers and service-operators) to record and submit logs/comments detailing issues in the website.
End User Documentation | Develop documents which will provide written support and details components of the system for end-users for their benefit.
Obtain Stakeholder Approval | To have a final meeting with our stakeholders and present them with our final product and obtain their final thoughts and requests for possible implementation.
Fix bugs | Fix any final bugs and issues which were produced from recent version.